## HOW TO USE
POWER-GIF MEAL Dashboard — Excel Data File
PURPOSE | This file feeds data directly into the POWER-GIF MEAL Dashboard HTML file.
Update data here → load file into dashboard → it refreshes instantly.
SHEETS | KPIs — Key performance indicators (current vs target)
Outcomes — Outcome-level indicator tracking
Activities — Activity / output progress (0–100 %)
Risks — Risk register with mitigation & level
HOW TO UPDATE | 1. Open this Excel file and go to the relevant sheet
2. Add or edit data starting from Row 4
3. Save the file (Ctrl + S)
4. Open the MEAL Dashboard in your browser
5. Click the green "Load from Excel" button
6. Select this file — dashboard updates immediately
RULES | • NEVER rename the sheet tabs
• NEVER move or edit rows 1–3 (title, headers, hint)
• Data always starts at Row 4
• Status must be exactly: On Track ¦ Needs Attention ¦ Delayed ¦ Not Started
• Risk Level must be exactly: High ¦ Medium ¦ Low
• Colour must be exactly: green ¦ amber ¦ red ¦ blue
• Completion % must be a number 0–100

## KPIs
POWER-GIF MEAL — KPI Data
KPI Label / Title | Current Value | Target Value | Unit (optional) | Colour (green/amber/red/blue) | Notes
Data starts here ↓ Do NOT edit rows 1–2
Industries surveryed/assessed | 10 | 120 | Industries | red
Policy Briefs | 0 | 7 | Reports | red
Clean energy and energy efficiency technologies | 0 | 5 | Technologies | red
Bankable Projects Identified | 0 | 5 | Projects | red
Pilot Demonstration Projects Deployed | 0 | 4 | Projects | red
Technical Training | 0 | 175 | Participants | red
GESI, OSH and PSHEA Training | 0 | 350 | Participants | red
Digital Platform | 0 | 1 | Application | red
PLC Deployment | 0 | 4 | Unit | red
BESS and Smart Grid Guideline | 0 | 1 | Report | red
Detailed Energy Assessment | 10 | 50 | Report | red

## Outcomes
POWER-GIF MEAL — Outcome Indicators
Outcome Area | Indicator Description | Baseline | Current Value | Target Value | Unit (optional) | Status | Notes
Data starts here ↓ Status dropdown: On Track ¦ Needs Attention ¦ Delayed ¦ Not Started
| Surplus electricity consumption | 0 |  | 17.5 | GWH | Not Started
| Feasibility Study of RE Projects | 0 |  | 10.96 | MW | On Track
| Industries Adopting EE technologies | 0 |  | 50 | industries | Not Started
| Fossil Fuel Reduction | 0 |  | 2027 | KL | Not Started
| GHG reduction ( CO2 e) | 0 |  | 6267 | tonnes | Not Started
| % decrease in energy intensity per unit production | 0 |  | 4.26% |  | Not Started
| Green jobs creation | 0 |  | 400 |  | Not Started
| Multi sector innovation and finance platform | 0 |  | 1 |  | Not Started
| Digital Transformation | 0 |  | 4 | PLC | Not Started
| BFI mobilising green funds | 0 |  | 5 | projects | Not Started
| Nepalese Skill enhancement | 0 |  | 1237 | people | Not Started

## Activities
POWER-GIF MEAL — Activity Progress
Activity Name | Location | Lead Partner / Person | Completion % (0–100) | Notes
Data starts here ↓ Completion % must be a number 0–100
1.1 Conduct Energy Transition Readiness assessment and develop a simulation based industrial energy transition roadmap in Birgunj Simara Industrial Corridor | Birgunj Simara corridor | CES | 9.375
1.2 Identify and evaluate sector specific fuel switching and clean energy pathways through baseliness assessment of the industrial sectors | Birgunj Simara corridor | CES | 17.25
1.3 Conduct Gender Responsive policy mapping and gap analysis of key strategic documents related to industries | Birgunj Simara corridor | CNI | 6.75
1.4 Develop concept note for policy and regulatory support for digital transformation and industrial productivity | Birgunj Simara corridor | CNI | 3
1.5 Develop concept note for policy and regulatory support for Clean and Green Energy Solutions Financing | Birgunj Simara corridor | CNI | 6.5
1.6 Conduct assessment of sustainable practices in Simara SEZ | SEZ Birgunj | AG | 21
1.7 Prepare the actionable recommendations to support inclusive Policy development for green industrial policy and fuel switching strategies | Birgunj Simara corridor | CNI | 3
2.1 Identify Viable and clean energy and energy efficient solutions | Birgunj Simara corridor | CRT | 4
2.2 Deploy pilot demonstration projects featuring optimal clean energy technologies | Birgunj Simara corridor | CRT | 0
2.3 Conduct gender responsive energy transition campaigns | Birgunj Simara corridor | CRT | 20.75
2.4 Facilitate fuelswitching and modernization of MSMEs by matching fund assistance (including mechanization and digitalization) | Birgunj Simara corridor | CRT | 1.25
3.1 Awareness Raising and orientation on CETs and Digitalisation | Birgunj Simara corridor | CRT | 2
3.2 Conduct a capacity needs assessment and deliver targeted training programs on energy auditing and energy management | Birgunj Simara corridor | CRT | 4
3.3 Support NEA on implementaiton of GESI Strategy 2021 | Kathmandu | NEA | 10
3.4 Develop and deliver training modules on GESI responsive workplace policies including decent work practices | Birgunj Simara corridor | CRT | 0
3.5 Establish and Institutionalise mentorship and peer learning networks | Birgunj Simara corridor | CNI | 24
3.6 Facilitate in establishing and operationalising a multi actor platform | Birgunj Simara corridor | CRT | 20
4.1 Develop a digital tool to map industrial energy transition pathways and track the progress | Birgunj Simara corridor | CRT | 2
4.2 Deployment of advance Programmable Logic Control (PLC) | Birgunj Simara corridor | CRT | 5
4.3 Development of digital platform for multi sectoral collaboration | Birgunj Simara corridor | CRT | 0
4.4 Operational Support to Energy Efficiency Learning Management System (EELMS) hosted by CES/IOE/TU | Lalitpur | CES | 0.75
5.1 Develop a preparatory design document to pilot smart green, resilient and inclusive grid concept at SimaraBirgunj industrial corridor | Birgunj Simara corridor | NEA | 17.5
5.2 Orient on potential financial instrument to uptake deployment of clean energy technology | Birgunj Simara corridor | CNI | 19
5.3 Stakeholder engagement and ecosystem building | Birgunj Simara corridor | CNI | 22.5
5.4 Leverge market based green and innovative financing mechanism | Birgunj Simara corridor | CNI | 3.5
5.5 Handholding support on accessing finance to adopt clean technology | Birgunj Simara corridor | CNI | 0

## Risks
POWER-GIF MEAL — Risk & Accountability Tracker
Risk Description | Mitigation Measure | Risk Level (High/Medium/Low) | Responsible Party | Notes
Data starts here ↓ Risk Level dropdown: High ¦ Medium ¦ Low
Lesser provision and schemes to green finance targeting CET. | Collaboration with like minded projects working under decarbonization of industries. | High | CNI
Lack of authorized vendors to implement/ maintain and after sales service of energy efficient and clean energy technogies. |  | High | CNI
Lack of industry readiness for CET adaptation | Rigorous interaction with relevant industries, development and dissemination of targeted communication packages | High | Project Team